## Daily Report Log
Daily Progress Report - Employee Management System (Farkhunda Memon)
Day | Date | Project | What did I complete? (previous day) | What am I working on today? | Blockers | GitHub Repo Link
WEEK 1
Day 1 | 2026-01-08 | Employee Management System | Set up development environment (Visual Studio 2026, XAMPP/MySQL, Git & GitHub). Created ASP.NET Core MVC project and connected it to a new GitHub repository. Designed and created the complete database in MySQL with 5 tables (Departments, Employees, Attendance, Leaves, Payroll) with proper foreign key relationships. Pushed initial project setup to GitHub. | Connect ASP.NET Core project to MySQL database and build the Employee module. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 2 | 2026-03-08 | Employee Management System | Completed database design (5 tables with relationships), created ASP.NET Core MVC project, connected project to MySQL database via Entity Framework, pushed all code to GitHub. | Building Employee module (full CRUD - Add, View, Edit, Delete) and Department module (full CRUD - Add, View, Edit, Delete) and Attendance Management module (full CRUD) using ASP.NET Core MVC. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 3 | 2026-04-08 | Employee Management System | Completed Employee module (full CRUD - Add, View, Edit, Delete) and Department module (full CRUD - Add, View, Edit, Delete) and Attendance Management module (full CRUD) using ASP.NET Core MVC. | Building Leave Management module and Payroll module (full CRUD, with automatic Net Salary calculation). Adding a navigation bar linking all modules and styling all List tables using Bootstrap for a professional UI look. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 4 | 2026-05-08 | Employee Management System | Completed all 5 core modules with full CRUD operations (Employee, Department, Attendance, Leave Management, Payroll - with automatic Net Salary calculation). Added a navigation bar linking all modules and styled all List tables using Bootstrap for a professional UI look. | Styled all Create/Edit forms with Bootstrap and built the Reports module with reports: Employees by Department, Payroll Summary, Leave Summary, and Attendance Summary and Updated the project repository on GitHub with the latest changes.. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 5 | 2026-06-08 | Employee Management System | Styled all Create/Edit forms with Bootstrap and built the Reports module with: Employees by Department, Payroll Summary, Leave Summary, and Attendance Summary. Pushed all updates to GitHub and created the ER Diagram for the database. | Redesigned the application with a new professional sidebar layout and dashboard Updated the Home/Dashboard page and Updated the project repository on GitHub with the latest changes | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 6 | 2026-07-08 | Employee Management System | Redesigned the application with a new professional sidebar layout and dashboard. Updated the Home/Dashboard page . | Created the database table for Admin login credentials in MySQL. Also finalized the SRS document. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 7 | 2026-08-08 | Employee Management System | Redesigned the application with a new professional sidebar layout and dashboard. Updated the Home/Dashboard page and started converting the Employee List page to the new design. | Built the Admin login system - created Admin model, updated AppDbContext, built AccountController with login logic, enabled Session in Program.cs, and designed the Login page. Also added a user info section and a unique Logout button in the sidebar navigation. |  | https://github.com/Farkhundamemon/Employee-Management-System
WEEK 2
Day 8 | 2026-10-08 | Employee Management System | Built the Admin login system - created Admin model, updated AppDbContext, built AccountController with login logic, enabled Session in Program.cs, and designed the Login page. Also added a user info section and a unique Logout button in the sidebar navigation. | Restyled the Add/Edit forms for Employee, Department, Attendance, and Payroll modules to match the new professional UI design | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 9 | 2026-11-08 | Employee Management System | Redesigned the application with a new professional sidebar layout and dashboard. Updated the Home/Dashboard page and started converting the Employee List page to the new design. | Built the complete Admin and Employee login system with session management. Created a separate Employee Portal where employees can view their own profile, attendance, leave history, and payslips, and submit new leave requests. Added Approve/Reject functionality for Admin on leave requests. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 10 | 2026-12-08 | Employee Management System | Built the complete Admin and Employee login system with session management. Created a separate Employee Portal where employees can view their own profile, attendance, leave history, and payslips, and submit new leave requests. Added Approve/Reject functionality for Admin on leave requests. | Redesigned the entire application UI to be more professional and attractive — updated the Admin Dashboard , redesigned all list pages (Employees, Departments, Attendance, Leaves, Payroll) with avatar icons, colored badges, and empty states, centered all forms , Implemented an Employee Status Management module — added Active/Deactivated/Terminated status , blocked login access for deactivated/terminated employees, and updated the Dashboard with new analytics cards (Active, Deactivated, Terminated counts). added a password visibility toggle on the Employee Edit form. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 11 | 13/8/2026 | Employee Management System | Implemented an Employee Status Management module (Active/Deactivated/Terminated) with a professional Change Status dropdown, blocked login for deactivated/terminated employees, updated Dashboard analytics, centered all Edit forms, added a password visibility toggle. | Rebuilt the Login page with a modern split-screen design and Performed complete end to end testing of the entire application Login system (Admin & Employee), Employee Status flow (Deactivate/Reactivate/Terminate with login blocking), all 5 core modules, the Leave Request workflow (Employee submits, Admin approves/rejects), and Payroll calculations all verified working. Also added a red notification badge on the sidebar showing pending leave request count, and expanded the Reports Module to 8 reports (added Active Employees, Deactivated Employees, Terminated Employees, and Department Summary reports). | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 12 | 14/8/2026 | Employee Management System | OFF |  | None
Day 13 | 15/8/2026 | Employee Management System | Performed complete end-to-end testing of the entire application, added a notification badge for pending leave requests, and expanded the Reports Module to 8 reports. | Finalized the SRS document (updated with Authentication Module, Employee Portal, and Status Management sections) and started working on the User Manual. | None | https://github.com/Farkhundamemon/Employee-Management-System
WEEK 3
Day 14 | 17/8/2026 | Employee Management System | Finalized the SRS document with updated sections for Authentication Module, Employee Portal, and Status Management. Started working on the User Manual. | Still working on the User Manual. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 15 | 18/8/2026 | Employee Management System | Continued working on the User Manual. | Also updated the Employee Portal based on feedback simplified it to show only Leave Requests and Payslips, removing detailed profile and attendance information for privacy. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 16 | 19/8/2026 | Employee Management System | Continued working on the User Manual. Also updated the Employee Portal based on feedback simplified it to show only Leave Requests and Payslips, removing detailed profile and attendance information for privacy. | Reviewing and planning an enhanced, industry-level database structure (Designations table, employee status audit history, leave approval tracking, and improved payroll fields) based on feedback received. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 17 | 20/8/2026 | Employee Management System | Reviewing and planning an enhanced, industry-level database structure (Designations table, employee status audit history, leave approval tracking, and improved payroll fields) based on feedback received. | Enhanced the database with Designations table, Leave Approval Tracking, Payroll improvements (Allowances, Gross Salary, Payment Status), and Reporting Manager field. Completed the User Manual and updated the SRS document with the Authentication Module, Employee Portal, Status Management sections, and a detailed Database Normalization (1NF-4NF) writeup. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 18 | 21/8/2026 | Employee Management System | Completed the User Manual and updated the SRS document with a detailed Database Normalization (1NF-4NF) section. | Reviewing remaining database enhancements for the Employee profile module (Employee Code, CNIC, Address, Emergency Contact, Employment Type, Department Head) and preparing Technical Documentation and Progress Report as per this week's requirements. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 19 | 22/8/2026 | Employee Management System | Reviewing remaining database enhancements for the Employee profile module (Employee Code, CNIC, Address, Emergency Contact, Employment Type, Department Head) and preparing Technical Documentation and Progress Report as per this week's requirements. | Extending the Employee profile with additional professional fields Employee Code, Gender, Date of Birth, CNIC, Address, Emergency Contact, Employment Type, and a Department Head field for Departments to align with the feedback for a more industry-level database structure and Made Employee Code auto-generate (EMP-001, EMP-002.) instead of manual entry, and fixed the database ER diagram by properly linking the newly added tables (Designations, Employee Status History, Reporting Manager, Department Head) with Foreign Keys.. | None | https://github.com/Farkhundamemon/Employee-Management-System
WEEK 4
Day 20 | 24/8/2026 | Employee Management System | Extending the Employee profile with additional professional fields Employee Code, Gender, Date of Birth, CNIC, Address, Emergency Contact, Employment Type, and a Department Head field for Departments to align with the feedback for a more industry-level database structure and Made Employee Code auto-generate (EMP-001, EMP-002.) instead of manual entry, and fixed the database ER diagram by properly linking the newly added tables (Designations, Employee Status History, Reporting | Start working on technical document | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 21 | 25/8/2026 | Employee Management System | Start working on technical documen | Exported the database SQL script for submission. Replacing all emoji icons across the application with modern, professional SVG line icons starting with the sidebar navigation and Dashboard stat cards, and continuing across all module pages for a more | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 22 | 27/8/2026 | Employee Management System | Exported the database SQL script for submission. Replacing all emoji icons across the application with modern, professional SVG line icons starting with the sidebar navigation and Dashboard stat cards, and continuing across all module pages for a more | Completed the Technical Documentation, User Manual, and updated SRS document. Also performing final end-to-end testing of the application, and fixed a couple of small issues found during testing removed the manual Employee Code field from forms (since it's now auto-generated), and added a password visibility toggle to the Employee Create form. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 23 | 28/8/2026 | Employee Management System | Completed the Technical Documentation, User Manual, and updated SRS document. Performed final end-to-end testing of the application and fixed remaining minor issues. | Building a new Designation Management module so Admin can add/edit job titles directly from the app instead of the database., Finalized the entire project and completed all remaining documentation and testing. | None | https://github.com/Farkhundamemon/Employee-Management-System
Day 24 | 29/8/2026 | Employee Management System |  |  | None | https://github.com/Farkhundamemon/Employee-Management-System